## Slide 1
Northstar maintenance portfolio - 30 September
Closed 48 + Cancelled 12 + Backlog 60 = 120. Recorded cost S$35,827.50; this is not a budget or saving.
Observation -> evidence -> proposed action -> decision
GenAI for Engineers v2.3 | Synthetic Northstar example | 2026-09-30 | All filters All | Slide1
Notes: Counts partition the selected source table exactly; recorded cost includes all statuses. Do not infer a budget or savings.

## Slide 2
50 of 60 backlog orders are overdue
On-time closure rate = 30/48 = 62.5%. Overdue backlog: 50, using Due_Date < 30 September 2026. Closed-only denominator, not all 120 orders.
Chart: 
| Woodlands Hub | Jurong Depot | Tampines Centre | Changi Workshop | Paya Lebar Office
Backlog work orders by site | 8 | 12 | 16 | 20 | 4
GenAI for Engineers v2.3 | Synthetic Northstar example | 2026-09-30 | All filters All | Slide2
Notes: Closed on/before Due_Date is on time. Numerator 30 and denominator 48 are both source-derived. A different scope must be recalculated.

## Slide 3
6 backlog orders need an assignment proposal
Unassigned backlog: 6. Compare primary category and available hours across 8 synthetic technicians. Current owners remain unchanged; specific suitable/approved allocations UNKNOWN.
Validate constraints before confirming an operational change.
GenAI for Engineers v2.3 | Synthetic Northstar example | 2026-09-30 | All filters All | Slide3
Notes: Six blank current owners are in backlog. Technicians table contains planning inputs, not approval or comprehensive safety/capacity evidence.

## Slide 4
Decision requested: review the proposed priorities
Requested decision: review and approve or revise the proposed recovery priorities and assignment checks. Decision owner, approval outcome and next review date UNKNOWN until supplied. No email sent and no source assignment changed.
Static presentation: verified snapshot, not an automatic live link.
GenAI for Engineers v2.3 | Synthetic Northstar example | 2026-09-30 | All filters All | Slide4
Notes: Ask for a decision without claiming one was made. The PowerPoint is a static snapshot; retain the interactive workbook and evidence register.