## About_This_Data
Field | Value
Company | Northstar Water Services - fictional water-pipe maintenance and service company
Reporting date | 2026-09-30
Scope | 120 Q3 2026 work orders, five sites. All identities and records are synthetic.
Meaning | Cost is cumulative recorded cost of all statuses; not a budget or productivity claim.
Rejoin | This input is a deterministic checkpoint, not proof of your Copilot output.

## Work_Orders
Work_Order_ID | Site | Job_Category | Priority | Status | Assigned_To | Opened_Date | Due_Date | Closed_Date | Estimated_Hours | Actual_Hours | Cost_SGD | Description
WO-2026-0001 | Woodlands Hub | Leak Repair | Low | Closed | Aisha Tan | 2026-09-25 | 2026-10-02 | 2026-09-30 | 2 | 1 | 90 | Leak Repair scheduled or reactive task 001
WO-2026-0002 | Woodlands Hub | Leak Repair | Medium | Closed | Ben Lim | 2026-09-24 | 2026-10-02 | 2026-09-30 | 3 | 2 | 125.5 | Leak Repair scheduled or reactive task 002
WO-2026-0003 | Woodlands Hub | Leak Repair | High | In Progress | Chloe Goh | 2026-09-23 | 2026-10-02 |  | 4 | 0 | 161 | Leak Repair scheduled or reactive task 003
WO-2026-0004 | Jurong Depot | Leak Repair | Critical | On Hold | Daniel Lee | 2026-09-22 | 2026-10-02 |  | 5 | 0 | 196.5 | Leak Repair scheduled or reactive task 004
WO-2026-0005 | Jurong Depot | Valve Repair | Low | New | Elena Ong | 2026-09-21 | 2026-10-02 |  | 6 | 0 | 232 | Valve Repair scheduled or reactive task 005
WO-2026-0006 | Jurong Depot | Valve Repair | Medium | Closed | Farid Rahman | 2026-09-20 | 2026-10-02 | 2026-09-30 | 7 | 6 | 267.5 | Valve Repair scheduled or reactive task 006
WO-2026-0007 | Tampines Centre | Valve Repair | High | Closed | Grace Ng | 2026-09-19 | 2026-10-02 | 2026-09-30 | 8 | 7 | 303 | Valve Repair scheduled or reactive task 007
WO-2026-0008 | Tampines Centre | Valve Repair | Critical | On Hold | Hari Kumar | 2026-09-18 | 2026-10-02 |  | 2 | 0 | 338.5 | Valve Repair scheduled or reactive task 008
WO-2026-0009 | Tampines Centre | Pipe Replacement | Low | New | Aisha Tan | 2026-09-17 | 2026-10-02 |  | 3 | 0 | 374 | Pipe Replacement scheduled or reactive task 009
WO-2026-0010 | Paya Lebar Office | Pipe Replacement | Medium | Cancelled | Ben Lim | 2026-09-16 | 2026-10-02 |  | 4 | 0 | 409.5 | Pipe Replacement scheduled or reactive task 010
WO-2026-0011 | Paya Lebar Office | Pipe Replacement | High | Closed | Chloe Goh | 2026-09-15 | 2026-09-22 | 2026-09-22 | 5 | 2 | 445 | Pipe Replacement scheduled or reactive task 011
WO-2026-0012 | Paya Lebar Office | Pipe Replacement | Critical | Closed | Daniel Lee | 2026-09-14 | 2026-09-22 | 2026-09-22 | 6 | 3 | 480.5 | Pipe Replacement scheduled or reactive task 012
WO-2026-0013 | Changi Workshop | Pump Service | Low | New |  | 2026-09-13 | 2026-09-22 |  | 7 | 0 | 516 | Pump Service scheduled or reactive task 013
WO-2026-0014 | Changi Workshop | Pump Service | Medium | Assigned | Farid Rahman | 2026-09-12 | 2026-09-22 |  | 8 | 0 | 90 | Pump Service scheduled or reactive task 014
WO-2026-0015 | Changi Workshop | Pump Service | High | In Progress | Grace Ng | 2026-09-11 | 2026-09-22 |  | 2 | 0 | 125.5 | Pump Service scheduled or reactive task 015
WO-2026-0016 | Woodlands Hub | Pump Service | Critical | Closed | Hari Kumar | 2026-09-10 | 2026-09-22 | 2026-09-23 | 3 | 7 | 161 | Pump Service scheduled or reactive task 016
WO-2026-0017 | Woodlands Hub | Meter Service | Low | Closed | Aisha Tan | 2026-09-09 | 2026-09-22 | 2026-09-23 | 4 | 8 | 196.5 | Meter Service scheduled or reactive task 017
WO-2026-0018 | Woodlands Hub | Meter Service | Medium | Assigned | Ben Lim | 2026-09-08 | 2026-09-22 |  | 5 | 0 | 232 | Meter Service scheduled or reactive task 018
WO-2026-0019 | Jurong Depot | Meter Service | High | In Progress | Chloe Goh | 2026-09-07 | 2026-09-22 |  | 6 | 0 | 267.5 | Meter Service scheduled or reactive task 019
WO-2026-0020 | Jurong Depot | Meter Service | Critical | Cancelled | Daniel Lee | 2026-09-06 | 2026-09-22 |  | 7 | 0 | 303 | Meter Service scheduled or reactive task 020
WO-2026-0021 | Jurong Depot | Leak Repair | Low | Closed | Elena Ong | 2026-09-05 | 2026-09-12 | 2026-09-14 | 8 | 3 | 338.5 | Leak Repair scheduled or reactive task 021
WO-2026-0022 | Tampines Centre | Leak Repair | Medium | Closed | Farid Rahman | 2026-09-04 | 2026-09-12 | 2026-09-14 | 2 | 4 | 374 | Leak Repair scheduled or reactive task 022
WO-2026-0023 | Tampines Centre | Leak Repair | High | In Progress | Grace Ng | 2026-09-03 | 2026-09-12 |  | 3 | 0 | 409.5 | Leak Repair scheduled or reactive task 023
WO-2026-0024 | Tampines Centre | Leak Repair | Critical | On Hold | Hari Kumar | 2026-09-02 | 2026-09-12 |  | 4 | 0 | 445 | Leak Repair scheduled or reactive task 024
WO-2026-0025 | Paya Lebar Office | Valve Repair | Low | New |  | 2026-09-01 | 2026-09-12 |  | 5 | 0 | 480.5 | Valve Repair scheduled or reactive task 025
WO-2026-0026 | Paya Lebar Office | Valve Repair | Medium | Closed | Ben Lim | 2026-08-31 | 2026-09-12 | 2026-09-10 | 6 | 8 | 516 | Valve Repair scheduled or reactive task 026
WO-2026-0027 | Paya Lebar Office | Valve Repair | High | Closed | Chloe Goh | 2026-08-30 | 2026-09-12 | 2026-09-10 | 7 | 9 | 90 | Valve Repair scheduled or reactive task 027
WO-2026-0028 | Changi Workshop | Valve Repair | Critical | On Hold | Daniel Lee | 2026-08-29 | 2026-09-12 |  | 8 | 0 | 125.5 | Valve Repair scheduled or reactive task 028
WO-2026-0029 | Changi Workshop | Pipe Replacement | Low | New | Elena Ong | 2026-08-28 | 2026-09-12 |  | 2 | 0 | 161 | Pipe Replacement scheduled or reactive task 029
WO-2026-0030 | Changi Workshop | Pipe Replacement | Medium | Cancelled | Farid Rahman | 2026-08-27 | 2026-09-12 |  | 3 | 0 | 196.5 | Pipe Replacement scheduled or reactive task 030
WO-2026-0031 | Woodlands Hub | Pipe Replacement | High | Closed | Grace Ng | 2026-08-26 | 2026-09-02 | 2026-09-01 | 4 | 4 | 232 | Pipe Replacement scheduled or reactive task 031
WO-2026-0032 | Woodlands Hub | Pipe Replacement | Critical | Closed | Hari Kumar | 2026-08-25 | 2026-09-02 | 2026-09-01 | 5 | 5 | 267.5 | Pipe Replacement scheduled or reactive task 032
WO-2026-0033 | Woodlands Hub | Pump Service | Low | New | Aisha Tan | 2026-08-24 | 2026-09-02 |  | 6 | 0 | 303 | Pump Service scheduled or reactive task 033
WO-2026-0034 | Jurong Depot | Pump Service | Medium | Assigned | Ben Lim | 2026-08-23 | 2026-09-02 |  | 7 | 0 | 338.5 | Pump Service scheduled or reactive task 034
WO-2026-0035 | Jurong Depot | Pump Service | High | In Progress | Chloe Goh | 2026-08-22 | 2026-09-02 |  | 8 | 0 | 374 | Pump Service scheduled or reactive task 035
WO-2026-0036 | Jurong Depot | Pump Service | Critical | Closed | Daniel Lee | 2026-08-21 | 2026-09-02 | 2026-09-02 | 2 | 9 | 409.5 | Pump Service scheduled or reactive task 036
WO-2026-0037 | Tampines Centre | Meter Service | Low | Closed | Elena Ong | 2026-08-20 | 2026-09-02 | 2026-09-02 | 3 | 1 | 445 | Meter Service scheduled or reactive task 037
WO-2026-0038 | Tampines Centre | Meter Service | Medium | Assigned | Farid Rahman | 2026-08-19 | 2026-09-02 |  | 4 | 0 | 480.5 | Meter Service scheduled or reactive task 038
WO-2026-0039 | Tampines Centre | Meter Service | High | In Progress | Grace Ng | 2026-08-18 | 2026-09-02 |  | 5 | 0 | 516 | Meter Service scheduled or reactive task 039
WO-2026-0040 | Paya Lebar Office | Meter Service | Critical | Cancelled | Hari Kumar | 2026-08-17 | 2026-09-02 |  | 6 | 0 | 90 | Meter Service scheduled or reactive task 040
WO-2026-0041 | Paya Lebar Office | Leak Repair | Low | Closed | Aisha Tan | 2026-08-16 | 2026-08-23 | 2026-08-24 | 7 | 5 | 125.5 | Leak Repair scheduled or reactive task 041
WO-2026-0042 | Paya Lebar Office | Leak Repair | Medium | Closed | Ben Lim | 2026-08-15 | 2026-08-23 | 2026-08-24 | 8 | 6 | 161 | Leak Repair scheduled or reactive task 042
WO-2026-0043 | Changi Workshop | Leak Repair | High | In Progress | Chloe Goh | 2026-08-14 | 2026-08-23 |  | 2 | 0 | 196.5 | Leak Repair scheduled or reactive task 043
WO-2026-0044 | Changi Workshop | Leak Repair | Critical | On Hold | Daniel Lee | 2026-08-13 | 2026-08-23 |  | 3 | 0 | 232 | Leak Repair scheduled or reactive task 044
WO-2026-0045 | Changi Workshop | Valve Repair | Low | New | Elena Ong | 2026-08-12 | 2026-08-23 |  | 4 | 0 | 267.5 | Valve Repair scheduled or reactive task 045
WO-2026-0046 | Woodlands Hub | Valve Repair | Medium | Closed | Farid Rahman | 2026-08-11 | 2026-08-23 | 2026-08-25 | 5 | 1 | 303 | Valve Repair scheduled or reactive task 046
WO-2026-0047 | Woodlands Hub | Valve Repair | High | Closed | Grace Ng | 2026-08-10 | 2026-08-23 | 2026-08-25 | 6 | 2 | 338.5 | Valve Repair scheduled or reactive task 047
WO-2026-0048 | Woodlands Hub | Valve Repair | Critical | On Hold | Hari Kumar | 2026-08-09 | 2026-08-23 |  | 7 | 0 | 374 | Valve Repair scheduled or reactive task 048
WO-2026-0049 | Jurong Depot | Pipe Replacement | Low | New |  | 2026-08-08 | 2026-08-23 |  | 8 | 0 | 409.5 | Pipe Replacement scheduled or reactive task 049
WO-2026-0050 | Jurong Depot | Pipe Replacement | Medium | Cancelled | Ben Lim | 2026-08-07 | 2026-08-23 |  | 2 | 0 | 445 | Pipe Replacement scheduled or reactive task 050
WO-2026-0051 | Jurong Depot | Pipe Replacement | High | Closed | Chloe Goh | 2026-08-06 | 2026-08-13 | 2026-08-11 | 3 | 6 | 480.5 | Pipe Replacement scheduled or reactive task 051
WO-2026-0052 | Tampines Centre | Pipe Replacement | Critical | Closed | Daniel Lee | 2026-08-05 | 2026-08-13 | 2026-08-11 | 4 | 7 | 516 | Pipe Replacement scheduled or reactive task 052
WO-2026-0053 | Tampines Centre | Pump Service | Low | New | Elena Ong | 2026-08-04 | 2026-08-13 |  | 5 | 0 | 90 | Pump Service scheduled or reactive task 053
WO-2026-0054 | Tampines Centre | Pump Service | Medium | Assigned | Farid Rahman | 2026-08-03 | 2026-08-13 |  | 6 | 0 | 125.5 | Pump Service scheduled or reactive task 054
WO-2026-0055 | Paya Lebar Office | Pump Service | High | In Progress | Grace Ng | 2026-08-02 | 2026-08-13 |  | 7 | 0 | 161 | Pump Service scheduled or reactive task 055
WO-2026-0056 | Paya Lebar Office | Pump Service | Critical | Closed | Hari Kumar | 2026-08-01 | 2026-08-13 | 2026-08-12 | 8 | 2 | 196.5 | Pump Service scheduled or reactive task 056
WO-2026-0057 | Paya Lebar Office | Meter Service | Low | Closed | Aisha Tan | 2026-07-31 | 2026-08-13 | 2026-08-12 | 2 | 3 | 232 | Meter Service scheduled or reactive task 057
WO-2026-0058 | Changi Workshop | Meter Service | Medium | Assigned | Ben Lim | 2026-07-30 | 2026-08-13 |  | 3 | 0 | 267.5 | Meter Service scheduled or reactive task 058
WO-2026-0059 | Changi Workshop | Meter Service | High | In Progress | Chloe Goh | 2026-07-29 | 2026-08-13 |  | 4 | 0 | 303 | Meter Service scheduled or reactive task 059
WO-2026-0060 | Changi Workshop | Meter Service | Critical | Cancelled | Daniel Lee | 2026-07-28 | 2026-08-13 |  | 5 | 0 | 338.5 | Meter Service scheduled or reactive task 060
WO-2026-0061 | Woodlands Hub | Leak Repair | Low | Closed | Elena Ong | 2026-07-27 | 2026-08-03 | 2026-08-03 | 6 | 7 | 374 | Leak Repair scheduled or reactive task 061
WO-2026-0062 | Woodlands Hub | Leak Repair | Medium | Closed | Farid Rahman | 2026-07-26 | 2026-08-03 | 2026-08-03 | 7 | 8 | 409.5 | Leak Repair scheduled or reactive task 062
WO-2026-0063 | Woodlands Hub | Leak Repair | High | In Progress | Grace Ng | 2026-07-25 | 2026-08-03 |  | 8 | 0 | 445 | Leak Repair scheduled or reactive task 063
WO-2026-0064 | Jurong Depot | Leak Repair | Critical | On Hold | Hari Kumar | 2026-07-24 | 2026-08-03 |  | 2 | 0 | 480.5 | Leak Repair scheduled or reactive task 064
WO-2026-0065 | Jurong Depot | Valve Repair | Low | New | Aisha Tan | 2026-07-23 | 2026-08-03 |  | 3 | 0 | 516 | Valve Repair scheduled or reactive task 065
WO-2026-0066 | Jurong Depot | Valve Repair | Medium | Closed | Ben Lim | 2026-07-22 | 2026-08-03 | 2026-08-04 | 4 | 3 | 90 | Valve Repair scheduled or reactive task 066
WO-2026-0067 | Tampines Centre | Valve Repair | High | Closed | Chloe Goh | 2026-07-21 | 2026-08-03 | 2026-08-04 | 5 | 4 | 125.5 | Valve Repair scheduled or reactive task 067
WO-2026-0068 | Tampines Centre | Valve Repair | Critical | On Hold | Daniel Lee | 2026-07-20 | 2026-08-03 |  | 6 | 0 | 161 | Valve Repair scheduled or reactive task 068
WO-2026-0069 | Tampines Centre | Pipe Replacement | Low | New | Elena Ong | 2026-07-19 | 2026-08-03 |  | 7 | 0 | 196.5 | Pipe Replacement scheduled or reactive task 069
WO-2026-0070 | Paya Lebar Office | Pipe Replacement | Medium | Cancelled | Farid Rahman | 2026-07-18 | 2026-08-03 |  | 8 | 0 | 232 | Pipe Replacement scheduled or reactive task 070
WO-2026-0071 | Paya Lebar Office | Pipe Replacement | High | Closed | Grace Ng | 2026-07-17 | 2026-07-24 | 2026-07-26 | 2 | 8 | 267.5 | Pipe Replacement scheduled or reactive task 071
WO-2026-0072 | Paya Lebar Office | Pipe Replacement | Critical | Closed | Hari Kumar | 2026-07-16 | 2026-07-24 | 2026-07-26 | 3 | 9 | 303 | Pipe Replacement scheduled or reactive task 072
WO-2026-0073 | Changi Workshop | Pump Service | Low | New |  | 2026-07-15 | 2026-07-24 |  | 4 | 0 | 338.5 | Pump Service scheduled or reactive task 073
WO-2026-0074 | Changi Workshop | Pump Service | Medium | Assigned | Ben Lim | 2026-07-14 | 2026-07-24 |  | 5 | 0 | 374 | Pump Service scheduled or reactive task 074
WO-2026-0075 | Changi Workshop | Pump Service | High | In Progress | Chloe Goh | 2026-07-13 | 2026-07-24 |  | 6 | 0 | 409.5 | Pump Service scheduled or reactive task 075
WO-2026-0076 | Woodlands Hub | Pump Service | Critical | Closed | Daniel Lee | 2026-07-12 | 2026-07-24 | 2026-07-22 | 7 | 4 | 445 | Pump Service scheduled or reactive task 076
WO-2026-0077 | Woodlands Hub | Meter Service | Low | Closed | Elena Ong | 2026-07-11 | 2026-07-24 | 2026-07-22 | 8 | 5 | 480.5 | Meter Service scheduled or reactive task 077
WO-2026-0078 | Woodlands Hub | Meter Service | Medium | Assigned | Farid Rahman | 2026-07-10 | 2026-07-24 |  | 2 | 0 | 516 | Meter Service scheduled or reactive task 078
WO-2026-0079 | Jurong Depot | Meter Service | High | In Progress | Grace Ng | 2026-07-09 | 2026-07-24 |  | 3 | 0 | 90 | Meter Service scheduled or reactive task 079
WO-2026-0080 | Jurong Depot | Meter Service | Critical | Cancelled | Hari Kumar | 2026-07-08 | 2026-07-24 |  | 4 | 0 | 125.5 | Meter Service scheduled or reactive task 080
WO-2026-0081 | Jurong Depot | Leak Repair | Low | Closed | Aisha Tan | 2026-09-25 | 2026-10-02 | 2026-09-30 | 5 | 9 | 161 | Leak Repair scheduled or reactive task 081
WO-2026-0082 | Tampines Centre | Leak Repair | Medium | Closed | Ben Lim | 2026-09-24 | 2026-10-02 | 2026-09-30 | 6 | 1 | 196.5 | Leak Repair scheduled or reactive task 082
WO-2026-0083 | Tampines Centre | Leak Repair | High | In Progress | Chloe Goh | 2026-09-23 | 2026-10-02 |  | 7 | 0 | 232 | Leak Repair scheduled or reactive task 083
WO-2026-0084 | Tampines Centre | Leak Repair | Critical | On Hold | Daniel Lee | 2026-09-22 | 2026-10-02 |  | 8 | 0 | 267.5 | Leak Repair scheduled or reactive task 084
WO-2026-0085 | Paya Lebar Office | Valve Repair | Low | New |  | 2026-09-21 | 2026-10-02 |  | 2 | 0 | 303 | Valve Repair scheduled or reactive task 085
WO-2026-0086 | Paya Lebar Office | Valve Repair | Medium | Closed | Farid Rahman | 2026-09-20 | 2026-10-02 | 2026-09-30 | 3 | 5 | 338.5 | Valve Repair scheduled or reactive task 086
WO-2026-0087 | Paya Lebar Office | Valve Repair | High | Closed | Grace Ng | 2026-09-19 | 2026-10-02 | 2026-09-30 | 4 | 6 | 374 | Valve Repair scheduled or reactive task 087
WO-2026-0088 | Changi Workshop | Valve Repair | Critical | On Hold | Hari Kumar | 2026-09-18 | 2026-10-02 |  | 5 | 0 | 409.5 | Valve Repair scheduled or reactive task 088
WO-2026-0089 | Changi Workshop | Pipe Replacement | Low | New | Aisha Tan | 2026-09-17 | 2026-10-02 |  | 6 | 0 | 445 | Pipe Replacement scheduled or reactive task 089
WO-2026-0090 | Changi Workshop | Pipe Replacement | Medium | Cancelled | Ben Lim | 2026-09-16 | 2026-10-02 |  | 7 | 0 | 480.5 | Pipe Replacement scheduled or reactive task 090
WO-2026-0091 | Woodlands Hub | Pipe Replacement | High | Closed | Chloe Goh | 2026-09-15 | 2026-09-22 | 2026-09-23 | 8 | 1 | 516 | Pipe Replacement scheduled or reactive task 091
WO-2026-0092 | Woodlands Hub | Pipe Replacement | Critical | Closed | Daniel Lee | 2026-09-14 | 2026-09-22 | 2026-09-23 | 2 | 2 | 90 | Pipe Replacement scheduled or reactive task 092
WO-2026-0093 | Woodlands Hub | Pump Service | Low | New | Elena Ong | 2026-09-13 | 2026-09-22 |  | 3 | 0 | 125.5 | Pump Service scheduled or reactive task 093
WO-2026-0094 | Jurong Depot | Pump Service | Medium | Assigned | Farid Rahman | 2026-09-12 | 2026-09-22 |  | 4 | 0 | 161 | Pump Service scheduled or reactive task 094
WO-2026-0095 | Jurong Depot | Pump Service | High | In Progress | Grace Ng | 2026-09-11 | 2026-09-22 |  | 5 | 0 | 196.5 | Pump Service scheduled or reactive task 095
WO-2026-0096 | Jurong Depot | Pump Service | Critical | Closed | Hari Kumar | 2026-09-10 | 2026-09-22 | 2026-09-24 | 6 | 6 | 232 | Pump Service scheduled or reactive task 096
WO-2026-0097 | Tampines Centre | Meter Service | Low | Closed | Aisha Tan | 2026-09-09 | 2026-09-22 | 2026-09-24 | 7 | 7 | 267.5 | Meter Service scheduled or reactive task 097
WO-2026-0098 | Tampines Centre | Meter Service | Medium | Assigned | Ben Lim | 2026-09-08 | 2026-09-22 |  | 8 | 0 | 303 | Meter Service scheduled or reactive task 098
WO-2026-0099 | Tampines Centre | Meter Service | High | In Progress | Chloe Goh | 2026-09-07 | 2026-09-22 |  | 2 | 0 | 338.5 | Meter Service scheduled or reactive task 099
WO-2026-0100 | Paya Lebar Office | Meter Service | Critical | Cancelled | Daniel Lee | 2026-09-06 | 2026-09-22 |  | 3 | 0 | 374 | Meter Service scheduled or reactive task 100
WO-2026-0101 | Paya Lebar Office | Leak Repair | Low | Closed | Elena Ong | 2026-09-05 | 2026-09-12 | 2026-09-10 | 4 | 2 | 409.5 | Leak Repair scheduled or reactive task 101
WO-2026-0102 | Paya Lebar Office | Leak Repair | Medium | Closed | Farid Rahman | 2026-09-04 | 2026-09-12 | 2026-09-10 | 5 | 3 | 445 | Leak Repair scheduled or reactive task 102
WO-2026-0103 | Changi Workshop | Leak Repair | High | In Progress | Grace Ng | 2026-09-03 | 2026-09-12 |  | 6 | 0 | 480.5 | Leak Repair scheduled or reactive task 103
WO-2026-0104 | Changi Workshop | Leak Repair | Critical | On Hold | Hari Kumar | 2026-09-02 | 2026-09-12 |  | 7 | 0 | 516 | Leak Repair scheduled or reactive task 104
WO-2026-0105 | Changi Workshop | Valve Repair | Low | New | Aisha Tan | 2026-09-01 | 2026-09-12 |  | 8 | 0 | 90 | Valve Repair scheduled or reactive task 105
WO-2026-0106 | Woodlands Hub | Valve Repair | Medium | Closed | Ben Lim | 2026-08-31 | 2026-09-12 | 2026-09-11 | 2 | 7 | 125.5 | Valve Repair scheduled or reactive task 106
WO-2026-0107 | Woodlands Hub | Valve Repair | High | Closed | Chloe Goh | 2026-08-30 | 2026-09-12 | 2026-09-11 | 3 | 8 | 161 | Valve Repair scheduled or reactive task 107
WO-2026-0108 | Woodlands Hub | Valve Repair | Critical | On Hold | Daniel Lee | 2026-08-29 | 2026-09-12 |  | 4 | 0 | 196.5 | Valve Repair scheduled or reactive task 108
WO-2026-0109 | Jurong Depot | Pipe Replacement | Low | New |  | 2026-08-28 | 2026-09-12 |  | 5 | 0 | 232 | Pipe Replacement scheduled or reactive task 109
WO-2026-0110 | Jurong Depot | Pipe Replacement | Medium | Cancelled | Farid Rahman | 2026-08-27 | 2026-09-12 |  | 6 | 0 | 267.5 | Pipe Replacement scheduled or reactive task 110
WO-2026-0111 | Jurong Depot | Pipe Replacement | High | Closed | Grace Ng | 2026-08-26 | 2026-09-02 | 2026-09-02 | 7 | 3 | 303 | Pipe Replacement scheduled or reactive task 111
WO-2026-0112 | Tampines Centre | Pipe Replacement | Critical | Closed | Hari Kumar | 2026-08-25 | 2026-09-02 | 2026-09-02 | 8 | 4 | 338.5 | Pipe Replacement scheduled or reactive task 112
WO-2026-0113 | Tampines Centre | Pump Service | Low | New | Aisha Tan | 2026-08-24 | 2026-09-02 |  | 2 | 0 | 374 | Pump Service scheduled or reactive task 113
WO-2026-0114 | Tampines Centre | Pump Service | Medium | Assigned | Ben Lim | 2026-08-23 | 2026-09-02 |  | 3 | 0 | 409.5 | Pump Service scheduled or reactive task 114
WO-2026-0115 | Paya Lebar Office | Pump Service | High | In Progress | Chloe Goh | 2026-08-22 | 2026-09-02 |  | 4 | 0 | 445 | Pump Service scheduled or reactive task 115
WO-2026-0116 | Paya Lebar Office | Pump Service | Critical | Closed | Daniel Lee | 2026-08-21 | 2026-09-02 | 2026-09-03 | 5 | 8 | 480.5 | Pump Service scheduled or reactive task 116
WO-2026-0117 | Paya Lebar Office | Meter Service | Low | Closed | Elena Ong | 2026-08-20 | 2026-09-02 | 2026-09-03 | 6 | 9 | 516 | Meter Service scheduled or reactive task 117
WO-2026-0118 | Changi Workshop | Meter Service | Medium | Assigned | Farid Rahman | 2026-08-19 | 2026-09-02 |  | 7 | 0 | 90 | Meter Service scheduled or reactive task 118
WO-2026-0119 | Changi Workshop | Meter Service | High | In Progress | Grace Ng | 2026-08-18 | 2026-09-02 |  | 8 | 0 | 125.5 | Meter Service scheduled or reactive task 119
WO-2026-0120 | Changi Workshop | Meter Service | Critical | Cancelled | Hari Kumar | 2026-08-17 | 2026-09-02 |  | 2 | 0 | 161 | Meter Service scheduled or reactive task 120

## Technicians
Technician | Primary_Category | Available_Hours_Week | Home_Site
Aisha Tan | Leak Repair | 35 | Woodlands Hub
Ben Lim | Leak Repair | 30 | Jurong Depot
Chloe Goh | Leak Repair | 35 | Tampines Centre
Daniel Lee | Leak Repair | 30 | Paya Lebar Office
Elena Ong | Valve Repair | 35 | Changi Workshop
Farid Rahman | Valve Repair | 30 | Woodlands Hub
Grace Ng | Valve Repair | 35 | Jurong Depot
Hari Kumar | Valve Repair | 30 | Tampines Centre

## Control
Metric | Expected / control
Report_Date | 2026-09-30
total | 120
closed | 48
cancelled | 12
backlog | 60
overdue | 50
unassigned_backlog | 6
on_time_closed | 30
on_time_rate | 0.625
cost | 35827.5
Backlog definition | Status is neither Closed nor Cancelled
Overdue definition | Backlog and Due_Date strictly earlier than Report_Date
On-time definition | Closed_Date <= Due_Date; denominator Closed only
Unknown assignment | Blank Assigned_To stays blank; propose separately

## Prompt_Log
Step | App / mode | Prompt | What Copilot did | How I verified | Decision
Step 1 | EXCEL - CHAT ONLY | EXCEL - CHAT ONLY: For the untouched 120-row Northstar Water Services baseline dashboard at 2026-09-30, All selectors, return a presentation evidence table: six KPIs, backlog by site, status and job-category counts, unassigned backlog and relevant source references. Do not use the refresh-test copy or infer service disruption, safety risk, causes or savings.
Step 2 | WORD COPILOT | WORD COPILOT: Using this verified 120-row Northstar maintenance snapshot, draft an eight-slide management presentation brief. For each slide give one claim headline, supporting measure/chart, source/date/scope, limitation and speaker note. Structure: overview, portfolio, site backlog, status/category mix, SLA/overdue, assignment/capacity, proposed actions/trade-offs, decision/next review. Do not invent causes, savings, approval or future dates; use UNKNOWN when absent.
Step 3 | WORD COPILOT | WORD COPILOT: Review this eight-slide Northstar Water Services brief against the supplied baseline evidence. Check each headline has a supporting value, correct units, source/date/scope and an explicit limitation. Rewrite unsupported claims as questions or proposed actions. Do not change verified figures or invent approvals.
Step 4 | POWERPOINT COPILOT | POWERPOINT COPILOT: @maintenance-reporting Create or update an eight-slide management presentation from the selected Northstar_Presentation_Brief.docx. Follow the existing white/navy/blue template. One evidence-based message per slide, short visible text, charts or tables for numerical evidence, source/as-at/scope in notes, and a final decision request. Keep values exact, and label all next actions as proposed. Do not add extra slides or invented facts.
Step 6 | POWERPOINT COPILOT | POWERPOINT COPILOT: Audit the eight-slide Northstar Water Services management draft against the selected presentation brief and evidence register. Confirm baseline 120, source notes, chart labels and units, correct backlog exclusions and proposed-action wording. List needed corrections and preserve slide count; do not claim Excel charts update automatically.

## Checks
Check | Formula / evidence | Result
Total clean rows

## Evidence_Log
Lab | Step | Claim_or_Test | Expected | Observed | Source_and_Scope | As_At | Verified_By | Notes

## .Rules
## SOURCE AND SCOPE
Preserve Work_Orders, tblWorkOrders, Technicians, current Assigned_To values and source IDs.
Use the reporting date from Control!B2. State the selected Site, Job_Category, Status and Assigned_To scope beside every report.
Backlog excludes Closed and Cancelled. Overdue backlog has Due_Date strictly before Control!B2.
On-time closure rate uses Closed rows only, with Closed_Date <= Due_Date. Display N/A when no Closed rows remain.
## FORMATS AND VISUALS
Display recorded Cost_SGD as S$ with two decimals; keep underlying values exact. Show dates as DD-MMM-YYYY.
Use white backgrounds, navy titles, blue and teal accents, readable labels and named units; never use colour alone.
## DASHBOARD LAYOUT
Dashboard sheet: title in A1; Site, Job_Category, Status and Assigned_To dropdowns in B2:B5 (All plus source values); the six measures in B7:B12; data-as-at date and selected scope in D2.
Six KPI tiles in D4:I7, one column per tile: title in row 4, large value in row 5, short definition in row 6 and "Checks: PASS" in row 7.
Charts in a grid below the tiles: work orders by status and by job category side by side, then a full-width stacked bar by site (overdue backlog, other backlog, Closed, Cancelled).
Slicers for Site, Job_Category, Status and Assigned_To on the right of the tiles, connected to tblWorkOrders. KPI formulas use SUBTOTAL visibility so slicers and dropdowns both filter every tile and chart.
Put chart summaries, chart-title formulas and KPI checks on Dashboard_Summaries. Never merge cells. Hide gridlines on Dashboard.
## DASHBOARD STYLE
Tiles: white bold text on solid navy #1F4E79 (totals and rates), blue #2E75B6 (backlog, overdue) or teal #2A9D8F (Closed, cost).
Every chart title states the finding from a cell formula, e.g. "Changi Workshop has the most overdue backlog (18 of 50)".
Show data labels on bars; no gridlines; rates as % with one decimal. Each chart total must equal B7.
## OUTPUT AND REVIEW
Use structured table references. Preserve the visible .Rules sheet and unrelated sheets, charts and Prompt_Log.
Keep current owners separate from unapproved assignment proposals. Missing facts and approvals remain UNKNOWN.
Ask before replacing named output sheets. Reconcile every count, rate and chart against source rows; do not duplicate outputs on rerun.

## Dashboard
Site | All
Job_Category | All
Status | All | Total work orders | Backlog | Overdue backlog | Closed | On-time closure rate | Recorded cost
Assigned_To | All
Measure | Current selection
Total work orders
Backlog
Overdue backlog
Closed
On-time closure rate
Recorded cost (S$)
Rows after slicers
How to filter
• Dropdowns B2:B5 or the slicers
both filter every tile and chart.
• Unassigned = blank Assigned_To.
• Baseline: all All, slicers cleared.
• Summaries + checks:
Dashboard_Summaries sheet.
This shape represents a table slicer. Table slicers need Excel 2013 or later.
This shape represents a table slicer. Table slicers need Excel 2013 or later.
This shape represents a table slicer. Table slicers need Excel 2013 or later.
This shape represents a table slicer. Table slicers need Excel 2013 or later.

## Dashboard_Summaries
Dashboard chart summaries, titles and checks (formula-backed; same selection as Dashboard)
Status | Work orders | Job category | Work orders | Site | Overdue backlog | Other backlog | Closed | Cancelled | Total | Item | Value
New |  | Leak Repair |  | Woodlands Hub | [5 empty] | Status chart title
Assigned |  | Valve Repair |  | Jurong Depot | [5 empty] | Category chart title
In Progress |  | Pipe Replacement |  | Tampines Centre | [5 empty] | Site chart title
On Hold |  | Pump Service |  | Paya Lebar Office | [5 empty] | Unassigned backlog
Closed |  | Meter Service |  | Changi Workshop | [5 empty] | Closed on or before due date
Cancelled |  | Total |  | Total | [5 empty] | Baseline view (All, no slicer)
Total | [9 empty] | Charts reconcile to B7
Check: total work orders
Check: backlog
Check: overdue backlog
Check: closed
Check: on-time rate
Check: recorded cost

## Filter_Lists (hidden)
All | All | All | All
Woodlands Hub | Leak Repair | New | Aisha Tan
Jurong Depot | Valve Repair | Assigned | Ben Lim
Tampines Centre | Pipe Replacement | In Progress | Chloe Goh
Paya Lebar Office | Pump Service | On Hold | Daniel Lee
Changi Workshop | Meter Service | Closed | Elena Ong
|  | Cancelled | Farid Rahman
Grace Ng
Hari Kumar
Unassigned