## Start_Here
Lab 2.2 — START HERE
Document both branches: the pass, and the fail with rectification and reinspection.
DO THIS FIRST
This file supplies the data only. Copy the Inspections and Rectification_Log sheets into your own Work-Order-Register.xlsx from Lab 2.1 (right-click the tab -> Move or Copy -> tick Create a copy), then work there. Nothing to import.
The sheets in this workbook
Inspections | The three supplied inspection rows, as the named table Inspections. Start here — select this table before opening Copilot.
Rectification_Log | The two supplied WO-022 rectification events.
Branch_Guide | The two branches after the Pass/Fail decision.
Check_Your_Work | The three variances to verify by hand: +42, -120, +18.
Copilot_Prompt | Both prompts, ready to copy without leaving Excel.
Amber cells are the ones you fill in.
Full steps and every Copilot prompt are in Lab-Instructions.pdf.
Synthetic training data. Fictional roadside drainage assets, people and criteria. Not a real operating limit or work authorisation.

## Inspections
Lab 2.2 · Inspection reports and rectification
Synthetic training data. Fictional roadside drainage assets, people and criteria. Not a real operating limit or work authorisation. The table below is named Inspections — select it before opening Copilot.
Work_Order | Inspection_Round | Timestamp_SGT | Worker | Asset | Silt_Depth_mm | Maximum_mm | Evidence_ID | Evidence_Description | Finding | Action | Source_Status | Margin_mm | Outcome | Evidence_Checked | Report_ID | Rectification_Status | Review_Note
WO-021 | Initial | 2026-09-18 10:00 | Amira Tan | DR-17 | 32 | 50 | EV-021-1 | Mock silt depth measured with a graduated rule, site log | Pass | None required | Synthetic training record
WO-022 | Initial | 2026-09-18 10:20 | Ben Lim | DR-23 | 74 | 50 | EV-022-1 | Mock silt depth measured with a graduated rule, site log | Fail | Desilt the drain section and reinspect | Synthetic training record
WO-022 | Reinspection | 2026-09-18 14:30 | Ben Lim | DR-23 | 28 | 50 | EV-022-2 | Mock post-desilting silt depth in the site log | Pass | Submit revised report for closure review | Synthetic training record

## Rectification_Log
Rectification log (supplied)
Fictional required/completed rectification events for WO-022.
Work_Order | Timestamp_SGT | Status | Actor | Record_ID | Action | Source_Status
WO-022 | 2026-09-18 11:00 | Rectification Required | Supervisor | RECT-022 | Desilt the drain section and reinspect | Synthetic training record
WO-022 | 2026-09-18 13:50 | Rectification Completed | Technician | RECT-022 | Desilting recorded as completed | Synthetic training record

## Branch_Guide
The two branches after the Pass/Fail decision
Record each state as its own row, in order. Keep earlier states.
Work order | Branch | States to record in order
WO-021 | Pass | Pass -> Generate Report -> Approval -> Closed
WO-022 | Fail | Fail -> Generate Report -> Rectification Required -> Rectification Completed -> Reinspection -> Pass -> Closed

## Check_Your_Work
Check the arithmetic by hand first
Verify these three variances before you accept any Copilot output.
Row | Silt depth | Maximum | Margin by hand | Outcome
WO-021 Initial | 32 | 50 | 50 - 32 = +18 within limit | Pass
WO-022 Initial | 74 | 50 | 50 - 74 = -24 over limit | Fail
WO-022 Reinspection | 28 | 50 | 50 - 28 = +22 within limit | Pass

## Copilot_Prompt
Prompts for Lab 2.2
Select the Inspections table first, then open Copilot in Excel.
EXCEL PROMPT Use only the selected Inspections table on the Inspections sheet. Preserve every Work_Order, Inspection_Round, timestamp, worker, asset, reading, unit, maximum, evidence ID and source status exactly as supplied. Add Margin_mm = Maximum_mm - Silt_Depth_mm for each of the three rows and show the arithmetic. A positive margin means the drain is within the limit. Set Outcome to Pass when Silt_Depth_mm is less than or equal to Maximum_mm, otherwise Fail. Keep all three rows visible, including WO-022's failed first inspection and its passing reinspection. Do not overwrite the first reading with the second. Mark missing real-world evidence as NOT SUPPLIED. Do not invent a root cause. End with DRAFT FOR ENGINEER REVIEW. WORD PROMPT (RPT-021.docx and RPT-022.docx) Using only the attached road lighting inspection table and the work order plan from Lab 2.1, draft two separate inspection reports. For each report include: scope; source records; factual observations; the comparison against the 50 mm criterion; evidence IDs; interpretation and limitations; an action and status table; and blank reviewer sign-off. For WO-021 report the 32 mm pass. For WO-022 retain 74 mm and EV-022-1 in the initial failure report, then add 28 mm and EV-022-2 in a clearly dated reinspection addendum labelled RPT-022-v2. The initial failure must stay visible in the versioned document. Do not assert an unproved cause, and do not record an actual approval. Mark DRAFT FOR ENGINEER REVIEW.